Mira — Program Charter

AI-Powered Project Intelligence Assistant · Nexora Pvt. Ltd. · Capstone: Applied Agentic AI for PMs/TPMs

Q3 submission · Author: Rosh

# 1. Vision

Mira exists so that Nexora's PM/TPMs spend their limited time on judgement calls instead of formatting. Every plan, risk matrix, and status report a PM currently builds by hand from a project's own files, Mira drafts to the same standard in minutes — grounded strictly in that project's own description, timeline, risk register, and task board, never in general knowledge. Success looks like a PM opening Mira, getting a client-ready first draft back before their coffee finishes brewing, and trusting it enough to spend their review time on judgement rather than fact-checking. The program earns that trust only by refusing to guess: a fast tool that invents a milestone is worse than no tool, because it hands the PM an unearned reviewing burden while appearing authoritative.

# 2. Scope

## In scope (v1)

- Project Plan Generation from a project description + timeline CSV (core)

- Risk Assessment producing a categorized matrix with impact and mitigation (core)

- Weekly Status Report from task board CSV, including blockers (core)

- Milestone Alert System — timeline vs. progress, flagging at-risk items (extended)

- Stakeholder Update Generator — audience-tailored narrative updates (extended)

- Request routing across all four request types, with refusal behavior on insufficient input

- Observability tracing, baseline evaluation against all 12 test cases, and cost analysis

## Out of scope (v1)

- Live Trello/Jira API integration — CSV upload only, to keep the auth surface at zero

- Writing back to any task board — Mira reads project systems, never mutates them

- Autonomous sending of client emails — all client-bound output requires PM approval

- Multi-project portfolio roll-up — v1 operates on one project's file set at a time

- Resource Allocation Advisor, Competitive/Market Analysis, and fine-tuning — deferred pending evaluation evidence that they're needed

# 3. Success Criteria

| # | Objective | Success Criterion (measurable) |
| --- | --- | --- |
| BO-1 | Cut plan-creation effort | Reduce 3–4 hrs of manual planning to under 30 min of review/edit on a generated draft |
| BO-2 | Cut status-reporting effort | Reduce 1–2 hrs weekly compilation to under 15 min |
| BO-3 | Standardize artefact format | 100% of generated plans, risk matrices, and status reports follow one defined schema |
| BO-4 | Make risk assessment consistent | Every active project has a categorized risk matrix with impact and mitigation |
| BO-5 | Surface slippage proactively | Blocked and at-risk items flagged before the retrospective, not during |
| BO-6 | Earn trust through correctness | Zero fabricated milestones, risks, tasks, or counts in any output shared with a client |

BO-6 is the governing constraint against which every other objective is subordinate — the program does not trade correctness for speed on any of the above.

# 4. Program Timeline

## Build (complete)

- Weeks 1–2: Ideation, business requirements, agent specification, and architecture design

- Weeks 2–3: Prompt engineering and individual agent build; each of the 3 core + 1 extended capability tested independently before wiring together

- Week 3: Full 12-case baseline test dataset run; 5 defects found via manual inspection and fixed (sprint-scoping, override-reading, refusal completeness, parallel-branch wiring, temperature)

- Week 4: Router/Dispatcher built to tie all agents together; Langfuse observability wired into all 5 workflow components; cost analysis grounded in real trace data; architecture writeup completed

## Rollout (proposed, gated by evidence not calendar)

- Phase 0 — Pilot: single PM (build owner), single project (ABCDE Ltd.), CSV-only inputs, every output human-reviewed before reaching the client. Exit gate: 2 consecutive weeks with zero fabricated facts in real usage, on top of the 12/12 baseline pass already achieved.

- Phase 1 — Team rollout: expand to Nexora's full PM/TPM team (up to 10), still one project's file set per Mira instance at a time. Exit gate: plan groundedness and status accuracy hold at their targets (100%) across at least 2 projects beyond ABCDE Ltd.

- Phase 2 — Steady state: quarterly review of the 3 production metrics (plan groundedness, risk relevance, status accuracy) plus refusal correctness. Any metric falling below target triggers a prompt fix-and-retest cycle, using the same evaluation loop already exercised during the build, before continued use.

# 5. Stakeholders

| Stakeholder | Relationship to Mira | What They Need |
| --- | --- | --- |
| PM/TPM at Nexora (primary user) | Runs 3–5 concurrent projects; uses Mira daily to draft plans, risk matrices, and status reports | A client-ready first draft in minutes, grounded strictly in the project's own files |
| Nexora Delivery Lead / CTO | Sponsors the program; consumes portfolio-level output | Consistent, comparable artefacts across all projects; visibility without chasing PMs |
| ABCDE Ltd. stakeholders (client) | Recipients of status reports and stakeholder updates | Accurate, professional, audience-appropriate updates they can trust |
| Nexora project team (named assignees) | Subjects of the task and resource data Mira reads | Fair, accurate representation of their workload and blockers |

# 6. Decision-Making & Governance

- Nexora CTO / Delivery Lead sponsors the program: approves scope changes, budget (negligible at this cost profile), and the go/no-go decision at each rollout phase gate.

- The build owner (PM/TPM responsible for Mira) owns technical and prompt-design decisions, and holds the line on BO-6: no change ships without passing the 12-case baseline test set.

- Individual PM/TPM users decide whether to adopt, edit, or discard any given draft — Mira never overrides a PM's judgement, and no client-bound output leaves the building without that PM's review (human-in-the-loop).

- Change control: any modification to a generating agent's prompt or the deterministic Data Prep logic must be re-validated against all 12 baseline cases before being considered shipped, mirroring the evaluate → fix → re-test loop used throughout the build.

# 7. Risks

| Risk | Mitigation |
| --- | --- |
| Building all agents before any single one works | Build and test one agent end-to-end first, then add the rest one at a time — already the pattern used in this build |
| Router misclassification silently corrupting downstream output | Log the intent label and reason in every trace; treat routing accuracy as its own measured metric |
| Observability deferred until the end of a project | Connect tracing in week 1 of any future agent addition — this build's own delay in doing so for the Router was a lesson learned |
| PM distrust after a single bad draft | Human-in-the-loop review plus source citation on every generated line, so trust is verifiable rather than assumed |
| Scope creep into optional extras (fine-tuning, live board APIs, market analysis) | Explicitly deferred unless evaluation evidence shows a specific, otherwise-unfixable failure |

# 8. Rollout Plan

Rollout proceeds in the three phases described in Section 4, gated on evidence rather than a fixed date: pilot with one PM and one project, expand to the full 10-person PM/TPM team once the pilot holds 100% groundedness and status accuracy for two consecutive weeks, then move to quarterly metric review at steady state. Each new PM's onboarding covers three things specifically: how to read a refusal (INSUFFICIENT_INPUT is correct behavior, not a bug), how to spot-check a draft using its source citations without re-deriving the underlying data by hand, and the standing rule that no client-bound artefact goes out without that PM's own review.